IIT GANDHINAGAR • WEEK 1, DAY 5 PM • POST-AGILE TEACHING BLOCK Agile in Action From Chaos to Clarity A contrast-based exercise — do the same task without Agile, then with it. Feel the difference.

## EXERCISE OVERVIEW

| Type | Guided → Semi-Guided Mix |
| --- | --- |
| Duration | ~75 minutes (fits in 2:00–3:30 PM practical block) |
| Group Size | Individual (Parts 1-3) → Groups of 4 (Part 4) |
| Materials | Paper/notebook, this handout, pen |
| Interview Relevance | Every L4+ PM/engineering interview asks 'How do you plan and track work?' |

How This Exercise Works

You'll do the same tasks twice — first without structure, then with Agile. The contrast is the lesson.

| Part | What You Do | Time | Mode |
| --- | --- | --- | --- |
| 1 | The Chaos Round — plan a project with zero structure | 10 min | Guided (individual) |
| 2 | The Agile Round — plan the SAME project using Agile | 15 min | Guided → Semi-Guided |
| 3 | Standup Showdown — give updates bad way vs BLUF way | 15 min | Guided → Practice |
| 4 | AI Mission Brief — full Agile planning for AI project | 25 min | Semi-Guided (groups) |
| 5 | Debrief — reflection + key takeaways | 10 min | Guided (cohort) |

PART 1 THE CHAOS ROUND 10 minutes • Guided — Individual

The Scenario

Your team has been asked to build an AI-powered campus food ordering system for IIT Gandhinagar. The mess committee wants students to:

▸  See the day's menu on their phone before meals

▸  Pre-order special items (limited quantity, first-come-first-served)

▸  Rate meals and give feedback (1-5 stars + comment)

▸  Get AI-suggested meals based on dietary preferences and past ratings

Timeline: 2 weeks to build and deploy.

Your Task (5 minutes — work alone, no templates)

On this page, answer these 4 questions. No frameworks, no structure. Just write whatever comes to mind.

1. What will you build? (describe the app in your own words)

An AI-powered food ordering app for the IIT Gandhinagar mess where students can view the daily menu, check timings, and see available special items. The app will allow students to pre-order limited items, track availability in real time, and make payments. It will also include a rating system for meals and provide AI-based recommendations based on past preferences and dietary choices

2. How will you split the work across your team?

- One developer will handle the frontend (UI and app interface) - One developer will handle the backend (database, APIs, order system) - The designer will create UI/UX layouts and user flows - The AI/ML engineer will work on the recommendation system - The PM will coordinate the team, track progress, and ensure deadlines are met

3. When will each part be done?

 First week: Complete development of core features (menu display, ordering, basic UI)  Next 3 days: Testing and fixing bugs internally  Next 2 days: Real-world testing with actual users and feedback  Final 2 days: Deployment and final adjustments

4. How will you know if you're on track?

A. By checking if development milestones are completed on time B. By reviewing progress regularly within the team C. By testing features after development to ensure they work correctly D. By verifying if the app is ready before the deployment deadline

🔍 CHECKPOINT — What the Trainer Will Surface After 3-4 students read their plans aloud, watch for these patterns (they WILL appear): ▸ "We'll build the whole thing first, then test" → Waterfall disguised as a plan ▸ "I'll do frontend, you do backend" → No shared understanding of scope ▸ "Should take about 2 weeks" → Pure guessing, no estimation methodology ▸ No mention of user feedback → Who validates you're building the right thing? ▸ Vague deliverables like "make the app" → What does "done" even mean? Key Takeaway: Every plan you just wrote is a waterfall plan in disguise.

PART 2 THE AGILE ROUND 15 minutes • Guided → Semi-Guided

Same project. Same 2 weeks. Same team. Now with Agile structure.

Step 1 — Write User Stories

Trainer demos this one: "As a student, I want to see today's menu on my phone before breakfast so that I can decide whether to eat at the mess or go outside." → 3 story points

Now you write 5 more. Use the exact format. Be specific — no vague stories.

Story Points Quick Reference 1 pt = Trivial (under 1 hour) → e.g., add a footer to the app 2 pts = Simple, clear path → e.g., display a static menu page 3 pts = Moderate, some decisions → e.g., meal rating system (stars + comment) 5 pts = Complex, multiple components → e.g., pre-order system with quantity limits 8 pts = Hard, significant unknowns → e.g., AI meal recommendations from past ratings

| # | User Story | Points |
| --- | --- | --- |
| 1 | As a student, I want to see today's menu on my phone before breakfast so that I can decide whether to eat at the mess or go outside. | 3 |
| 2 | As a user, I want to receive AI-based meal recommendations based on my past ratings and preferences so that I can choose meals I will likely enjoy. | 8 |
| 3 | As a user, I want to view meal timings along with the menu so that I know when each meal is served. | 2 |
| 4 | As a user, I want to pre-order special items with limited quantity so that I can secure my meal before it runs out. | 5 |
| 5 | As a user, I want to see real-time availability of special items so that I know whether they are still in stock. | 3 |
| 6 | As a user, I want to rate meals and leave comments so that I can provide feedback on food quality. | 3 |

Step 2 — Sprint Planning

You have 2 weeks = 2 sprints. Assign your stories to sprints. Sprint 1 capacity ≤ 15 points (unknown velocity — start conservative).

SPRINT 1 (Week 1)  —  Goal: ____ Deliver usable system + admin control____________________________________

| Story # | User Story (short version) | Points | Owner |
| --- | --- | --- | --- |
| 1 | View daily menu | 3 | Frontend + Backend |
| 2 | View meal timings | 2 | Frontend |
| 7 | Staff updates menu & quantities | 5 | Backend |
| 5 | Rate meals + comments | 3 | Frontend + Backend |
| 1 | View daily menu | 3 | Frontend + Backend |
| TOTAL |  | __ / 15 |  |

SPRINT 2 (Week 2)  —  Goal: ________________________________________

| Story # | User Story (short version) | Points | Owner |
| --- | --- | --- | --- |
| 4 | View real-time availability | 3 | Backend |
| 3 | Pre-order special items | 5 | Frontend + Backend |
| Buffer | Testing + deployment stabilization | 5 | Team |
| TOTAL |  | _13_ / 15 |  |

Step 3 — Compare Your Two Plans

Look at your Chaos Round plan (Part 1) and your Agile plan (Part 2) side by side. Answer honestly.

| Question | Chaos Round | Agile Round |
| --- | --- | --- |
| Can you tell what 'done' looks like for Week 1? | No — only “build phase” is defined, no concrete deliverable. | Yes — working app with menu, timings, ratings, and admin control. |
| Could a new team member join and understand the plan? | No — plan is vague and role-based, lacks structure. | Yes — user stories, sprint goals, and ownership make it clear. |
| When does the mess committee first SEE something working? | Around Day 10–12 (after build phase) | End of Week 1 (after Sprint 1 delivery) |
| If you fall behind by Day 3, how quickly would you know? | Late — no checkpoints, issues surface during testing phase | Early — daily tracking and sprint scope make delays visible immediately |
| Can you identify the riskiest part of the project? | No — all work treated equally | Yes — AI recommendations (8 points, high uncertainty) |

The Difference Should Be Obvious One plan is a wish. The other is a system. Agile doesn't add more work — it adds more CLARITY about what the work actually is.

PART 3 THE STANDUP SHOWDOWN 15 minutes • Guided → Live Practice

Round A — The Bad Standup (Trainer reads aloud)

The Bad Update (read this in a mumbling, vague tone) "Yeah so... I've been working on the project. It's going okay I think. I did some stuff with the menu page. I'll keep working on it. No blockers."

What's wrong with this? (call out the problems as a class)

| Problem | Why It's Bad |
| --- | --- |
| No specifics | What "stuff"? What menu page? Which part of it? |
| No evidence | No commit, no screenshot, no test result |
| "I think" | You don't actually know your own status |
| "Keep working on it" | No plan for today — just vibes |
| "No blockers" | Either lying or hasn't thought about it |

Round B — Rewrite It Using BLUF (3 min — individual)

Same scenario: It's Wednesday of Sprint 1. You've been working on the food ordering app for 3 days. Rewrite the update properly.

OPENING (10 sec) Yesterday I completed: What was the specific task? What's the evidence (commit hash, screenshot, test passing)?

Implemented the Menu screen UI and menu-fetch flow; pushed commit 3a7f2b1 and opened PR #14 (screenshot in PR). Unit tests for MenuCard pass locally (3/3).

DETAIL (20 sec) Specifically, I: What exactly did you do? Name the files, the functions, the feature.

 Added src/screens/MenuScreen.js and src/components/MenuCard.jsx.  Implemented api/menu.js::fetchMenu() to call GET /api/menu/today.  Updated mock mocks/menu.json and wrote tests/menucard.test.js.  CSS adjustments in styles/menu.css and accessibility labels for menu items.

TODAY (15 sec) Today I'm working on: What specific task? Expected output? By when?

 Add meal timings display under each menu item and show available_quantity.  Update integration tests to assert presence of serving_times and available_quantity.  Expected output: timings rendered in MenuCard, integration tests green, and push a follow-up PR by EOD Wednesday.

BLOCKER (15 sec) I'm blocked on: What's the problem? What have you tried? What do you need from someone?

Round C — Live Practice (Groups of 4 — 8 min)

1.  Form groups of 4 (closest neighbors) — STAND UP

2.  Each person delivers their BLUF update from Round B

3.  TIMER: 90 seconds per person. Timekeeper CUTS YOU OFF at 90.

4.  After all 4 go → group picks: Who gave the clearest update? Why?

5.  3 volunteers deliver to the full cohort (1 min each)

| Criteria | What to Look For |
| --- | --- |
| Specificity | Did they name exact tasks — not vague 'stuff'? |
| Evidence | Did they mention a commit, screenshot, or test result? |
| Time awareness | Did they estimate when today's work would be done? |
| Honest blockers | Did they ask for help — or claim 'no blockers' dishonestly? |
| BLUF structure | Did they lead with the main point, not bury it? |
| Delivery | Eye contact, clear voice, no filler words, under 90 sec? |

PART 4 AI MISSION BRIEF 25 minutes • Semi-Guided — Groups of 4

This is where it all comes together. A realistic AI project — plan it end-to-end using Agile.

CLIENT BRIEF Client: A mid-size EdTech company with 500 students across 3 cohorts. Problem: Students submit assignments via email, Google Forms, and WhatsApp — no single system. Faculty waste 6+ hours/week hunting for submissions. Late submissions slip through. Students game the system ("I sent it but it didn't reach you"). Build an AI-Powered Assignment Submission & Tracking System that: ▸ Accepts submissions via a single web portal ▸ Auto-validates: correct file format, file size, naming convention ▸ Timestamps every submission (tamper-proof) ▸ Uses an LLM to auto-generate a 2-line summary of each submission ▸ Flags potential plagiarism by comparing similarity across submissions ▸ Sends automated reminders 2 hours before deadline ▸ Provides a faculty dashboard showing submission status per student Constraints: 4 engineers • 3 sprints of 1 week each • Python + any LLM API + any DB • Must deploy (not localhost)

## DELIVERABLE 1 — User Stories (Write at least 8)

| # | User Story | Pts | Priority |
| --- | --- | --- | --- |
| 1 | As a student, I want to submit assignments through a web portal so that all submissions are centralized in one system. | 5 | Must |
| 2 | As a system, I want to timestamp every submission automatically so that deadlines are enforced fairly and cannot be manipulated. | 3 | Must |
| 3 | As a system, I want to validate file format, size, and naming conventions so that submissions follow required rules. | 5 | Must |
| 4 | As a faculty member, I want to view all submissions in a dashboard so that I can track who has submitted and who hasn’t. | 5 | Must |
| 5 | As a student, I want to receive a confirmation after submission so that I know my assignment was successfully received. | 2 | Must |
| 6 | As a system, I want to send automated reminders before deadlines so that students submit on time. | 3 | Should |
| 7 | As a faculty member, I want AI-generated summaries of submissions so that I can quickly understand each assignment. | 8 | Should |
| 8 | As a faculty member, I want to detect similarity between submissions so that potential plagiarism can be flagged. | 8 | Could |

Priority Guide Must = Without this, the system is useless (e.g., file upload, timestamp) Should = Important but system works without it (e.g., LLM summaries) Could = Nice-to-have, cut first if behind (e.g., plagiarism detection)

## DELIVERABLE 2 — Sprint Plan

Your team velocity for Sprint 1 = ~20 story points (4 people × 5 pts each, conservative). Don't overcommit.

SPRINT 1  —  Goal: _ End-to-end assignment submission working (upload → validate → timestamp → visible to faculty______________________________________________

(What is the ONE thing that must work by end of this sprint?)

| Story # | Short Description | Pts | Owner | Definition of Done |
| --- | --- | --- | --- | --- |
| 1 | File upload via web portal | 5 | Eng A (Backend) + Eng C (Frontend) | File successfully uploaded via UI and stored in server |
| 2 | Automatic timestamping | 3 | Eng D (DB/Infra) | Timestamp stored in DB and visible in API response |
| 3 | File validation (format/size/naming) | 5 | Eng A | Invalid files rejected with proper error messages |
| 4 | Faculty dashboard (basic list) | 5 | Eng C | Faculty can see list of submissions with timestamps |
| TOTAL |  | _20_/20 |  |  |

SPRINT 2  —  Goal: System reliability + student compliance (reminders + improved visibility)

(What is the ONE thing that must work by end of this sprint?)

| Story # | Short Description | Pts | Owner | Definition of Done |
| --- | --- | --- | --- | --- |
| 6 | Automated deadline reminders | 3 | Eng D | Students receive reminder 2 hrs before deadline |
| 4 (enhanced) | Dashboard with status (submitted/not) | 5 | Eng C | Faculty sees per-student submission status |
| Hardening | Error handling + logging | 5 | Eng A | System handles failures gracefully, logs errors |
| Deployment | Cloud deployment (live URL) | 5 | Eng D | App accessible via public URL (not localhost) |
| TOTAL |  | _23_/25 |  |  |

SPRINT 3  —  Goal: ___ Goal: AI augmentation (summaries) + optional intelligence____________________________________________

(What is the ONE thing that must work by end of this sprint?)

| Story # | Short Description | Pts | Owner | Definition of Done |
| --- | --- | --- | --- | --- |
| 7 | LLM summaries | 8 | Eng B | Each submission shows 2-line summary |
| 8 | Plagiarism detection | 8 | Eng B + Eng A | Similarity score shown for submissions |
| Optimization | Performance tuning | 4 | Eng D | System handles 500 students without lag |
| UI polish | Dashboard improvements | 3 | Eng C | Clean UI, filters, better UX |
| TOTAL |  | 23/25 |  |  |

## DELIVERABLE 3 — Risk Register

What could go wrong? Identify at least 4 risks. Two are pre-filled as examples.

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| LLM API rate limits hit during bulk submission period | H | H | Queue requests + batch processing + fallback summary |
| Plagiarism detection has too many false positives | M | M | Set threshold + manual review flag instead of auto-penalty |
| File upload failures under peak load | M | H | Use cloud storage (S3/GCS) + retry mechanism |
| Deadline reminder system fails (cron/job issues) | M | H | Add monitoring + backup trigger system |
| Deployment issues (env/config mismatch) | M | H | Use Docker + staging environment before production |
| Students upload incorrect formats intentionally | H | M | Strict validation + clear error messaging |

## DELIVERABLE 4 — Day 3 Standup Role-Play

It's Day 3 of Sprint 1. Each team member picks a role and writes a realistic standup update. Then deliver it to your group — standing up, 90 seconds, timed.

ENGINEER A — Backend / API Focuses on: file upload endpoint, validation logic, database schema

Yesterday I completed: Implemented file upload endpoint with validation logic

Evidence (commit / screenshot / test): Commit a1b9c3, Postman tests passing (200 OK + validation errors working)

Today I'm working on: Integrating timestamp storage with DB

Expected done by: EOD today

Blocker (if any): Waiting on DB schema finalization from Eng D

ENGINEER B — LLM Integration Focuses on: submission summary generation, prompt engineering, API calls

Yesterday I completed: Tested LLM API for summarization with sample inputs

Evidence (commit / screenshot / test): Notebook output + API response logs saved

Today I'm working on: Designing prompt for consistent 2-line summaries

Expected done by: Tomorrow noon

Blocker (if any): Need sample real submissions for better prompt tuning

ENGINEER C — Frontend / Dashboard Focuses on: student upload page, faculty dashboard, status indicators

Yesterday I completed: Built upload page UI and connected to backend API

Evidence (commit / screenshot / test): PR #21 + working UI demo

Today I'm working on: Faculty dashboard (submission list view)

Expected done by: EOD tomorrow

Blocker (if any): Need API response format finalized

ENGINEER D — Database / Deployment Focuses on: database setup, deployment pipeline, timestamp system

Yesterday I completed: Set up PostgreSQL schema for submissions

Evidence (commit / screenshot / test): Schema commit + local DB running

Today I'm working on: Timestamp integration + deployment pipeline setup

Expected done by: Tomorrow

Blocker (if any): None

## DELIVERABLE 5 — Sprint 1 Review Script

It's the end of Sprint 1. Write your demo script — what do you show the client?

COMMITMENT: "Here's what we committed to this sprint:" List your sprint goal + the stories you planned

We committed to delivering a working submission system with validation, timestamping, and faculty visibility.

REALITY: "Here's what we actually delivered:" Be honest — what's DONE vs what didn't make it?

✅ File upload working ✅ Validation implemented ✅ Timestamp stored ✅ Dashboard basic version ready ⚠ Minor UI polish pending

LIVE DEMO: "Let me show you it working:" What would you show running? Be specific.

- Upload assignment via portal - Show validation rejection (wrong file) - Successful upload → confirmation - Faculty dashboard → shows submission + timestamp

LEARNINGS: "What we learned / What changed:" Scope adjustments? Technical discoveries? Estimate corrections?

- File validation edge cases more complex than expected - API-frontend contract needs earlier alignment - Deployment took longer than estimated

NEXT SPRINT: "Sprint 2 preview:" What's next? Any re-prioritization needed?

- Add reminders - Improve dashboard visibility - Deploy stable production version

PART 5 DEBRIEF + FAST FINISHER STRETCH 10 minutes • Guided — Cohort

Personal Reflection (2 min — write silently)

1. What was the single biggest difference between planning without Agile and planning with it?

Without Agile, planning was vague and assumption-driven — I couldn’t clearly define progress or detect issues early. With Agile, work is broken into measurable units with clear deliverables, making progress, risks, and priorities visible from the start.

2. What's the ONE thing about standups that will be hardest for you personally? Why?

Being specific with evidence. Because it forces real accountability — I can’t hide behind vague statements like “I worked on it.” I need to know exactly what I completed, what changed, and what the outcome was.

3. Starting tomorrow — what specific Agile behavior will you adopt for Project AdmitGuard?

I will define clear “Definition of Done” before starting any task and give daily updates in BLUF format with measurable outputs.

FAST FINISHER STRETCH — The Curveball

SCOPE CHANGE (For groups that finish Part 4 early) You're 2 days into Sprint 2. The client walks in and says: "We just realized we also need the system to work with WhatsApp submissions — some faculty refuse to stop using WhatsApp. Can you add a WhatsApp bot that accepts submissions via message?" This is a scope change mid-sprint. What do you do?

| Strategy | What You'd Say to the Client |
| --- | --- |
| NEGOTIATE | "We can add it, but something else moves out of Sprint 2. Which current feature is lower priority?" |
| DEFER | "We'll add it to the backlog and plan it for Sprint 3. Here's why: [reason]." |
| SPIKE | "We'll do a 2-hour investigation to check feasibility, then give you an honest estimate." |
| ACCEPT (rarely right) | "We'll absorb it." — Only if team has slack AND it's truly critical. |

Your team's response:

Strategy chosen: DEFER + SPIKE

What we'd say to the client (exact words): “We understand the importance of WhatsApp integration. Since we’re mid-sprint, adding it now would impact committed delivery. We propose doing a quick feasibility spike and scheduling it for Sprint 3.”

Why this strategy (what are we optimizing for?): A. Protect sprint commitment B. Reduce risk before committing C. Maintain delivery reliability

The Real Skill The skill isn't saying 'yes' or 'no' — it's saying 'yes, AND here's the tradeoff.' This is one of the most common real-world situations in Agile teams. Interviewers at Amazon, Google, and Uber specifically test for this.

## SCORING RUBRIC

This exercise contributes to today's session participation (Labs & GitHub WPS component).

| Criteria | Points | What's Assessed |
| --- | --- | --- |
| User Stories quality | 30 | Specific? INVEST criteria met? Story points reasonable? |
| Sprint Plan completeness | 25 | Goals clear? Points within velocity? Definition of Done stated? |
| Standup quality (live) | 25 | BLUF format? Specific? Under 90 sec? Evidence mentioned? |
| Risk Register + Scope | 10 | Realistic risks? Thoughtful mitigation? Curveball handled well? |
| Participation | 10 | Spoke up in group? Explained reasoning? Engaged in sprint review? |

What Happens Next ✓ Daily standups start at 5:30 PM today — use the BLUF format from Part 3 ✓ Saturday's Project AdmitGuard showcase = your first Sprint Review ✓ Fill the standup prep template BEFORE every standup for the next 19 weeks ✓ By Week 18, you'll have done 100+ standups — that's 100 reps of a skill most candidates fake ✓ When an interviewer asks 'How do you plan work?' — you'll answer from experience, not a textbook

IIT Gandhinagar  •  PG Diploma in AI-ML & Agentic AI Engineering  •  Week 1 Day 5